## Sheet1
Risk Management Table
Risk Summary | Risk Category | Probability | Impact(1-4) | RMMM
Poor Quality of documentation | BU | 15% | 1 | If any topic is missing in documentation, it can be added afterwards.
Quality assurance, Speed of the software | TI | 20% | 2 | The quality of software is much better afterwards and each of the module of software can communicate mutually and properly.
Delivery Deadline | BU | 25% | 2 | The cost associated with a late delivery is critical. Steps must have to be taken based on scope of project delivery deadline.
Size in line of codes | Product size | 25% | 3 | as size of code increases, the size of the software increases too.
database instability | TI | 35% | 2 | The possible errors may come due to poor error-checking .The error causing issues should be highlighted to the members so that they can improvise the software and its facilities.
Change in requirement | PS | 30% | 2 | It helps in meeting up the requirements of the customer which the developer is trying to satisfy.
Software interface | TE | 20% | 1 | Software that enables it to continue operating reliably on interface.
Technology to be built is new for developer | TE | 25% | 2 | If the technology is new , then the developers would need time to connect and adapt to the new technology. If learnt hastily, then it might lead to faulty development of software.