## Sheet1
Task | Start Date | Day to Complete
Analysis of requirement | 2018-01-02 | 20
Making abstract or prototype | 2018-01-18 | 12
Design wireframe | 2018-01-29 | 21
Implement project with database | 2018-02-20 | 22
Software Testing | 2018-03-02 | 14
Analysing issues or feedback | 2018-03-12 | 12
Changes according to feedback | 2018-03-25 | 9